## Runbook
30 Acts of Kindness - release runbook
Release: Thursday 1 October 2026, 7:00 AM Central (8:00 AM Eastern). Claude gives each command at the time, one at a time.
How to use: when a step is finished, click its cell in the Done column and pick ✓ from the list. The row turns green.
Progress: 3 of 35 steps done
Done | Step | When | Where | What to do | How you know it worked
TUESDAY 29 / WEDNESDAY 30 SEPTEMBER - preparation (only you, David and the testers can see any of this)
✓ | 1 | Tue | PowerShell | Check both logins: npx eas whoami ; npx supabase projects list | Both show you logged in; the list includes mtfyekdxtkdiaqbgaoza.
✓ | 2 | Tue | PowerShell | Check the code is clean: git status ; git log -1 --oneline | "working tree clean".
✓ | 3 | Tue | Claude + Chrome | Website (item 29): App Store button, Android waitlist. Checked in Chrome and committed (9ec89f2). NOT uploaded until Thursday. | Page looked right; committed.
| 4 | Wed | Phone / text | Optional (item 65): find one person with an iPhone that never had the app and a number with no account, for the influencer-link test. | Someone agreed - or skip; the link uses the same code as the app's invite links.
WEDNESDAY - reminders deploy (items 27, 28, 51, 52, 61, 66). Approved 29 Sep. Safe at every step: after the deploy the old key still works, so no reminder is missed.
| 5 | Wed | PowerShell | Deploy the new reminders code: npx supabase functions deploy send-reminders --project-ref mtfyekdxtkdiaqbgaoza | "Deployed Function send-reminders".
| 6 | Wed | Supabase production - SQL Editor | Wait for the next 5-minute tick, then run Claude's check query. | Status 200 (old key still works).
| 7 | Wed | Supabase production - SQL Editor | Create the door secret inside Vault (Claude's query; the database generates it, so it never appears in chat). | The query returns the new secret's id.
| 8 | Wed | Supabase production - SQL Editor, then Edge Functions > Secrets | Read the secret from Vault, copy it (never paste it into chat) and add it as REMINDERS_DOOR_SECRET. | The secret is listed.
| 9 | Wed | Supabase production - SQL Editor | Show cron job 7's command; Claude writes the replacement that reads the secret from Vault; run it. | Command updated.
| 10 | Wed | Supabase production - SQL Editor | Wait for the next tick and run the check query again. | Status 200. (If 401: put the old command back - Claude keeps it.)
WEDNESDAY - 1.0.1 update, then the sign-in hook (items 41, 43, 15, 18, 53, 54, 67, 17c-app, 59). Approved 29 Sep. The update MUST go first: the old sign-in screen does not ask for a code.
| 11 | Wed | PowerShell, in 30-Acts-current | Publish 1.0.1: npx eas update --branch production --environment production -m "1.0.1" | "Published!" with an update id. Send Claude the id.
| 12 | Wed | iPhone - production 30 Acts app | Open it, wait 10 seconds, swipe it closed, open it again. | The build stamp at the bottom of Settings shows the new update.
| 13 | Wed | iPhone | Settings > Privacy Policy. | It says "Effective: October 1, 2026".
| 14 | Wed | Supabase production - Authentication > Hooks | Customize Access Token > Postgres > schema public > require_otp_for_password_login > Enable. | The hook shows Enabled.
| 15 | Wed | iPhone | Sign out, then sign back in. | It texts you a code and you land in your own account.
| 16 | Wed | Text to David and the testers | "Please open 30 Acts, close it and open it again to get today's update. You stay signed in." | Each sees the update.
THURSDAY 1 OCTOBER - release day (times are Central)
| 17 | 6:45 | Laptop | Open tabs: App Store Connect (30 Acts of Kindness > Distribution), Supabase production, GoDaddy cPanel File Manager, Twilio, Sentry. | All open and signed in.
| 18 | 6:50 | Supabase production - SQL Editor | Run Claude's check query on the overnight reminder ticks. | All 200.
| 19 | 7:00 | App Store Connect | Press Release This Version, then confirm. | "Processing for Distribution", then "Ready for Distribution".
| 20 | 7:05 | Supabase production - Authentication > Rate Limits | Rate limit for sign-ups and sign-ins: change 30 to 150. Change nothing else. Save. | It shows 150 requests/5 min.
| 21 | every 15 min | iPhone Safari | Open https://apps.apple.com/app/id6762151038 | The app page shows a Get button (minutes to a few hours).
THURSDAY - once the app shows in the App Store
| 22 |  | iPhone | Delete and reinstall (you only). Press and hold 30 Acts of Kindness - NOT 30 Acts (Staging), keep that one - then Remove App > Delete App. Install it again from the App Store link. | Installed from the App Store.
| 23 |  | iPhone | Open it, wait 10 seconds, swipe it closed, open it again. Do NOT sign in before the reopen - the first launch runs the old code, which the hook refuses. | The second launch shows the new sign-in screen.
| 24 |  | iPhone | Sign in with your number and the texted code. | Your acts, streak and tree are all there.
| 25 |  | Text to David and the testers | "30 Acts is live! Install it from https://apps.apple.com/app/id6762151038 over your TestFlight copy (if it only offers Open, delete the app first - your account is safe). Open, close, reopen, then sign in with the text code. Keep 30 Acts (Staging)." | Each confirms.
| 26 |  | GoDaddy cPanel File Manager - public_html | Website (items 29, 17c-web): upload index.html, site.js and privacy.html from 30-Acts-current\website, replacing the old ones. | 30actsofkindness.org shows the App Store button; the privacy page says October 1, 2026. Check on your phone too.
| 27 |  | Test person's iPhone | Optional (item 65): they open your test Branch link, install, sign up. Claude gives a query to confirm the credit. | The influencer's number shows as the inviter.
THURSDAY - after the website is live
| 28 |  | Email / Messages | Waitlist messages (item 64): send all 12 from Desktop\Waitlist launch messages.txt, including David Schwartz's "Android is coming" email. He stays on the waitlist, which is now the Android waitlist. | All 12 sent.
| 29 |  | Email / Messages | Your contacts and David's. | Sent.
| 30 |  | Instagram, Facebook, LinkedIn, X, YouTube, TikTok | Launch post with the graphics on your Desktop (influencer-30acts-*.png) pointing to 30actsofkindness.org. Switch TikTok to the 30 Acts account first. | Posted on all six.
| 31 |  | Branch dashboard, then Claude | Influencers (item 65): for each, create a Quick Link (alias = their name, link data ref = +1 and their 10 digits, iOS fallback id6762151038). Send Claude the name and link; Claude makes their 3 graphics with their QR code and their captions. | Each influencer has their link, graphics and captions.
| 32 | all day | Twilio, Sentry, Supabase | Watch: Twilio error 30007 (carrier filtered); Sentry new or "Regressed" issues; Supabase reminder ticks 200. Tell Claude anything odd. | Nothing unexplained.
| 33 | end of day | Claude | Update the backlog and write the handoff. | Done.
FRIDAY 2 OCTOBER OR LATER
| 34 |  | App Store Connect, then Supabase production - SQL Editor | Downloads tile (item 42): Apps > 30 Acts of Kindness > Analytics > Overview > First-Time Downloads, "Last 7 days" (about a day behind). Send Claude the number; run the one-line SQL Claude gives. | The Admin Downloads tile shows the real number.
| 35 | after 5 Oct | TikTok app | Change the TikTok name from 30actsofkind to 30 Acts of Kindness (item 69). | Name updated.

## If something goes wrong
If something goes wrong
What happened | What to do
A reminder tick returns 401 after the cron change | Put cron job 7's previous command back (Claude keeps it). Reminders resume at the next tick.
Nobody can sign in after the hook is enabled | Supabase production > Authentication > Hooks > Disable. Sign-in works as before. Then tell Claude.
The 1.0.1 update misbehaves | Tell Claude before doing anything else. A fix or a rollback goes out the same way as the publish step.
The App Store page takes hours to appear | Normal. Nothing in the "once the app shows" section starts until it does.
Wednesday's steps did not all get done | Do the rest on Thursday: reminders deploy before 7:55 CT; the 1.0.1 update and hook right after Release This Version; then the rate limit.